| P.21-16 |  |  |  | King’s Lynn Library Project Highlight Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Name: |  | King’s Lynn Library |  |  |  | Project Manager |  |  | Verity Bennett |  |  | Project Sponsor: |  |  |  | Sarah Rhoden |  |  |  |  |  | Report covers period of: |  |  |  | March 2026 |  |
| Capital Code: |  |  | C8435 |  |  |  |  | Client Dept: |  |  |  | NCC Community Services |  |  |  |  |  | Lead Designer: |  |  |  |  | Hudson Architects |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Cost Consultant: |  |  |  |  | Turner and Townsend |  |  |  |  |
| Project Code: |  |  | P.21-16 |  |  |  |  | End User (if applicable: |  |  |  | King’s Lynn residents and visitors to the town |  |  |  |  |  | Contractor on Site: |  |  |  |  | Mace |  |  |  |  |
| Management Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 1.Overall Status |  |  | 2.1 Risks |  |  |  | 2.2. Issues |  |  | 3.Financials |  |  |  |  |  | 4.Timelines |  |  |  | 5.Resources |  |  |  |
| This Report |  |  |  | G |  |  | G |  |  |  | G |  |  | G |  |  |  |  |  | G |  |  |  | G |  |  |  |
| Last Report |  |  |  | A |  |  | A |  |  |  | G |  |  | G |  |  |  |  |  | G |  |  |  | G |  |  |  |
| Project Definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Stage: RIBA Stage 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objectives: - Develop a co-located ‘community multi-use hub’ facility in the town centre of King’s Lynn - Provide skills and educational opportunities for residents starting at entry level. Develop new community adult learning education and higher education courses that meet skills needs in the Town. - Develop new community partnerships to provide a variety of programming and community support offers from the hub - Provide services and facilities for start-ups and local businesses |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Scope: To create a modern, accessible library, learning, and community hub in the heart of King’s Lynn town centre. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Overall Status (high-level summary) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall RAG status is GREEN - The library has opened to the public! |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Decisions required by the Neighbourhood Board |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - No decisions required this month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Achievements during this period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The library successfully opened to the public on Monday 16th March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Risks and Issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Key Risks [all red and increasing amber] – something that may happen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Risk ID (0/25) | Risk Title |  |  | Description |  |  |  |  |  | RAG Status |  |  | Risk Category |  |  |  | Mitigation |  |  |  |  |  |  |  |  |  | Dated Comments |
| 2.2 Key Issues [all red and increasing amber] – something that has happened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Issue ID (0/2) | Issue Title |  |  | Description |  |  |  |  |  | RAG Status |  |  |  |  | Issue Type |  |  |  | Resolution Plan |  |  |  |  |  | Dated Comments |  |  |
| Note: further detail on Project Risks and Issues can be found in the Risks and Issues Log. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Note: will vary for each project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Financial Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 Financial Commentary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The Financial RAG rating is GREEN - Total project actuals to date are £17.3m against an updated budget of £17.3m and is on budget. Some minor costs are still expected over the coming months along with some credit notes for flooring and other. - Overall, the project is forecasted to be on budget at £17.3m - Costs in this financial year total £12.5m, with prior year costs totalling £4.8m. - The funding from the Town Deal fund was £7.4m and £9.9m from Norfolk County Council, totalling £17.3m. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Project Contingency and Change Control |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Change Ref |  | Description |  |  |  | Cost Impact |  |  | Programme Impact |  |  | Other Impact |  |  |  | RAG Status |  |  |  |  |  | Approval given by |  |  |  | Date of change |  |
| N/A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| 4. Timelines – High Level Milestones |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4.1 Timelines Commentary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The library has opened to the public |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Resources Commentary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources remain GREEN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Communications and Engagement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - The library successfully opened its doors on Monday 16th March. - The first week we welcomed 8297 visitors (compared to 911 on the equivalent week last year) - Book issues for week one was up 277% and new member registrations up 2661% - We have been running tours of the new facilities, and these have been fully booked every day since opening. - Clubs restart in the library w/c 30th March and Adult Learning courses start properly after Easter. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Outputs and Outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcomes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description |  |  |  |  |  |  |  | Target |  |  |  |  | Notes |  |  |  |  |  |  |  |  |  |
| Amount of capacity of new or improved training or education facilities |  |  |  |  |  |  |  | 5,200 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of learners enrolled in new education and training courses |  |  |  |  |  |  |  | 100pa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of learners / trainees / students enrolled at improved education and training facilities |  |  |  |  |  |  |  | 350pa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of learners/students/trainees gaining certificates, graduating or completing courses at new or improved training or education facilities, or attending new courses |  |  |  |  |  |  |  | 100pa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # of potential entrepreneurs assisted to be enterprise ready |  |  |  |  |  |  |  | 32pa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Improved perceptions of place by residents, visitors, and businesses |  |  |  |  |  |  |  | 70% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Increased footfall to the town centre |  |  |  |  |  |  |  | 200,000 pa25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outputs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description |  |  |  |  |  |  |  |  |  |  | Targets |  |  |  |  |  |  | Notes |  |  |  |  |
| Number of new cultural facilities |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |
| Number of derelict buildings refurbished |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |
| Number of public amenities / facilities created` |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  | 1 |  |  |  |  |
| Amount of new office space – meeting rooms and hot desking |  |  |  |  |  |  |  |  |  |  | 400sqm |  |  |  |  |  |  | 400sqm |  |  |  |  |
| Amount of floor space repurposed (commercial) – spaces available for commercial hire |  |  |  |  |  |  |  |  |  |  | 425sqm |  |  |  |  |  |  | 425sqm |  |  |  |  |
| # of transport nodes with new multimodal connection points |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |  |  |
| 8. Other Matters |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |  |  | Comment |  |  |  |  |  |  |  |  |  |  |  |
| General stage progress |  |  |  |  |  |  |  |  |  |  | RIBA Stage 5, Construction |  |  |  |  |  |  |  |  |  |  |  |
| Procurement progress |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  |
| Proposed form of contract (e.g. JCT, NEC, Traditional, D&B) |  |  |  |  |  |  |  |  |  |  | JCT Design and Build (D&B) |  |  |  |  |  |  |  |  |  |  |  |
| Proposed route to market (e.g. IOTT, Framework i.e. DPS, HPCS, LCP) |  |  |  |  |  |  |  |  |  |  | Framework |  |  |  |  |  |  |  |  |  |  |  |
| Legal progress |  |  |  |  |  |  |  |  |  |  | Exchange and Completion on building complete |  |  |  |  |  |  |  |  |  |  |  |
| ICT, FF&E update |  |  |  |  |  |  |  |  |  |  | FF&E development in progress |  |  |  |  |  |  |  |  |  |  |  |
| Stakeholder engagement (comms) |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  |
| Local schemes / dependencies |  |  |  |  |  |  |  |  |  |  | Concept study of Baxter’s Plain public realm (outside scope of MUCH) |  |  |  |  |  |  |  |  |  |  |  |
| 9. Approved Documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | OBC [RIBA 0 Approval] |  | Client Brief [RIBA 1 Initiation] |  | Resource Brief |  |  |  | PID [RIBA 1 Gateway] |  | PID Update [RIBA 2 Gateway] |  | PID Update [RIBA 3 Gateway] |  |  |  |  |  |  | PID Update [RIBA 4 Design) | Final PID [pre-post tender] |
| Status: |  | ✔ |  | ✔ |  | ✔ |  |  |  | ✔ |  | ✔ |  | ✔ |  |  |  |  |  |  | ✔ | ✔ |
| Date Approved: |  |  |  | Sept 22 |  | Nov 22 |  |  |  | May 23 |  | July 23 |  | Jun 24 |  |  |  |  |  |  | Jun 25 |  |
| Approved by: |  |  |  | TDB |  | TDB |  |  |  | PB |  | PB |  | PB |  |  |  |  |  |  | PB |  |
| Last approved document: PID May 2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Spend – Budget variance (Inc. Contingency) |  |  |  |  |  |  | Milestone Delivery RAG Status |  |  |  |  |  |  |  | Risk & Issue RAG status |  |  |  |  |  |  |  |
| R | More than 10% over or under budget |  |  |  |  |  | R |  | 13 weeks or more behind the critical path |  |  |  |  |  | R |  | Need immediate attention |  |  |  |  |  |
| A | Between 5% & 10% over or under budget |  |  |  |  |  | A |  | 4 to 12 weeks behind the critical path |  |  |  |  |  | A |  | Needs attention before next project review |  |  |  |  |  |
| G | Within 5% of budget or less than £10k |  |  |  |  |  | G |  | 4 to 12 weeks less behind the critical path |  |  |  |  |  | G |  | Can be managed |  |  |  |  |  |