## Town Deal Projects
No. | Project | Brief description | RAG ratings as at end of March 2026 (Direction of travel indicated) | Overall status commentary
P-21.11 | St George’s Guildhall & Creative Hub | • Redevelopment and refurbishment of St George’s Guildhall, from road to river, into a fully working theatre • To establish a cultural hub, which will be a heritage visitor attraction, education resource, and commercial hub by day, and a theatre and entertainment venue by night | Overall RAG rating | Overall RAG Status this month is AMBER • Main Contract Works – Scaffold erection across the site is ongoing. Roof to Guildhall is nearing completion, despite challenges with the first burst water mains on King Street. The design team continues to release key information in line with the IRS schedule. No delays reported at this stage. Sunday 1st March – initial repairs to first water leak in King Street failed. Reactions by MCL/ team now underway – insurance claim being prepared. • Fundraising - Historic England Grant works are well underway, second payment received (£151k) and final payment (£295k) has been requested. Various monthly performance, evaluation outputs are due next month. The award also conditions that the BC will spend c£525k by end of June 2026 on specific ongoing or new scoped works. These works are planned in to the works schedule. • Party wall - Despite continuous efforts, scaffold licenses/ party wall agreements to Wetherspoons & 2+3 Ferry Lane are still unsigned. Wetherspoons are not responding to escalated requests. 2+3 Ferry Lane are seeking unreasonable demands. BC legal back to back with these issues and preparing for possible enforcement next steps. These delays are now impacting MCL who seek to flex their programme to work-around things but time is now getting critical. • Interpretation Works – Immersive experience consultant tender period is nearly completed, and results have been issued to tenderers. Following the February meeting with the Interpretation designer (PLB) preparation is under way for the immersive consultants join the team. • King Street public realm – Pre-App Public engagement runs 23 March – 17th April. 25th public drop in event at Nos 29. Late April. May final review before submission to planning (possibly PD) and highways. • Crown Post Truss Peter McCurdy/ Momentum contracted to design the truss and connections strategy. MCL being asked to complete heritage works and installation in house given experience.
A
P-21.12 | Active & Clean Connectivity | • To deliver the vision of promoting active travel as a safe and attractive modal option, reducing congestion and improving air quality • Package of measures to support active & clean connectivity including priority schemes from the Local Cycling & Walking Infrastructure Plan (LCWIP) including the Active Travel Hub and Travel Plan Fund | Overall RAG rating | Overall RAG Status is AMBER • Active Travel Hub Enterprise Zone –Planning permission denied for Baker Lane Active Travel Hubs at March 2026 committee. Lead Local Flood Authorities (LLFA) requested extension to consultation period for King’s Lynn Enterprise Park (KLEP) Active Travel Hub (ATH) placing application with report to reach committee in May 2026. • LCWIP – Final LCWIP scheme to deliver crossing at Gayton Road complete and final accounts due in April 2026. • Active Travel Plans – Work ongoing with College of West Anglia (CWA) and Queen Elizabeth Hospital (QEH). • With the remaining budget, the project team are assessing options for additional activities to encourage active travel in 2026.
A
P-21.14 | Riverfront Regeneration | • Development of designs to enable the Riverfront area to become an attractive destination space increasing footfall, promoting day and nighttime use, facilitating events etc. • Renovation of the Custom House, improvements to King’s Staithe Square, south quay public realm and land surrounding Devils Alley | Overall RAG rating | Overall RAG Status is AMBER • The Devil’s Alley component of the project will now proceed under the Pride in Place (PiP) Programme funding. • A Project Adjustment Request has been submitted to MHCLG, formalising the revised scope, outputs, and funding allocations. • As part of this adjustment, £2 million will be reallocated from the Riverfront Regeneration to the St George’s Guildhall and Creative Hub project. Guidance on completing this process is expected shortly. • Updated Business Plan and Economic Case to reflect the new scope has been prepared with a preferred option for Custom House identified. • A comprehensive reprogramming exercise has also been carried out to align the project timeline while keeping as close to original programme as possible. • Planning permission and listed building consent granted for both the Custom House and Dryside. • Works to the Dryside started in January and are due to be completed in July 2026. • A historical accounting issue identified that impacted the remaining available budget has sought resolution through the wider programme underspend and funding re-allocation (£595k). Following approval, the capital project is now fully funded.
A
P-21.15 | Public Realm – ‘Rail to River’ | • Improve public realm in the town centre to improve the pedestrian experience, removing clutter, creating consistent public realm experience • Rail to River route works include providing interventions such as pop-up facilities, art trail, fingerpost wayfinding, lighting, seating and planting. | Overall RAG rating | Overall RAG Status is GREEN • Whilst Pop Up spaces became available for hire in March 2025, promotion was paused due to street‑level scaffold works that limited access. Interim uses continue in the meantime; a relaunch is planned for spring 2026. • Artwork, seating, fingerposts and a digital wayfinding sign have all been successfully installed. • Fourteen trees and custom planters have been placed along Purfleet Street, New Conduit Street, and Broad Street. • Management of the Pop Ups has now moved to the Operations Team, while responsibility for the digital signage sits with the Marketing and Communications Team. • The Purfleet Street Arch is the only outstanding element. Progression was paused due to fire damage of the building where installation was planned alongside issues getting the licence signed for its installation. An options paper on pursing the the arch install or exploring alternatives will be appended to the Post Project Evaluation.
G
P-21.16 | King's Lynn Library (Multi-User Community Hub) | • To create a modern, accessible library, learning, and multi-use community hub in the heart of King’s Lynn town centre, including skills and educational opportunities, community support offers and services and facilities for start-ups and local businesses | Overall RAG rating | Overall RAG status is GREEN • The library has opened to the public!
G